## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Data Team | 2026-02-10 | Incomplete collection of historical email datasets from primary sources | Sprint 1 | Data Team | Logical | Re-fetched data from alternative enterprise email repositories | 2026-02-14 | Closed | Validated during Sprint 1 review
2 | Data Team | 2026-02-12 | Preprocessing script failed to normalize text for non-standard signatures | Sprint 1 | Data Team | Standards | Updated regex patterns to include international signature formats | 2026-02-15 | Closed | Accuracy improved for noise removal
3 | ML Team | 2026-02-18 | Category classification model showing low recall for 'complaints' category | Sprint 2 | ML Team | Logical | Tested multiple models (Logistic Regression vs. Random Forest) to find better fit | 2026-02-21 | Closed | Final model achieved > 85% recall
4 | ML Team | 2026-02-24 | NLP model confidence scores below threshold for multi-class classification | Sprint 2 | ML Team | Logical | Optimized hyperparameters and augmented training data for minority classes | 2026-02-28 | Closed | Confidence scores reached target > 90%
5 | ML Team | 2026-03-02 | Urgency prediction module incorrectly tagging technical requests as 'low' urgency | Sprint 3 | ML Team | Logical | Integrated rule-based keywords with the ML classification logic | 2026-03-07 | Closed | Urgency tags now match business rules
6 | Frontend Team | 2026-03-10 | Real-time dashboard latency exceeds 5 seconds for new email events | Sprint 4 | Frontend Team | User Interface | Optimized WebSocket connection and reduced frontend state update frequency | 2026-03-14 | Closed | Latency reduced to < 1 second
7 | Frontend Team | 2026-03-16 | Dashboard category filters returning null results for 'feedback' selection | Sprint 4 | Frontend Team | User Interface | Debugged UI filtering logic and synchronized state with API response | 2026-03-21 | Closed | Filters verified as working correctly
8 | Platform Team | 2026-03-23 | API integration timeout when processing emails with large attachments | Sprint 5 | Platform Team | User Interface | Configured asynchronous processing for email attachments in the cloud | 2026-03-28 | Closed | Connection stable for all sizes
9 | Platform Team | 2026-03-25 | Live Streamlit deployment crashing under concurrent user stress tests | Sprint 5 | Platform Team | Maintainability | Optimized in-memory model cache and upgraded instance resource limits | 2026-03-30 | Closed | System stable in production
10 | ML Team | 2026-03-05 | Stopwords removal script stripping essential domain-specific keywords | Sprint 3 | ML Team | Standards | Curated a custom stopwords exclusion list for enterprise domain jargon | 2026-03-08 | Closed | Improved context retention in modeling

## Sheet2
Logical
User Interface
Maintainability
Standards
Others